## Implementation Checklist
PDCA Implementation Checklist
Track each implementation step from project definition through sustainment.
# | PDCA Phase | Checklist Item | Why It Matters | Owner | Due Date | Status | Completion Summary
1 | PLAN | Define the problem using facts and data | Prevents vague improvement work |  |  | Not Started | Total Items | 14
2 | PLAN | Document baseline performance | Creates a comparison point |  |  | Not Started | Completed | 0
3 | PLAN | Validate likely root cause | Avoids treating symptoms |  |  | Not Started | Completion % | 0%
4 | PLAN | Set a SMART target | Clarifies success criteria |  |  | Not Started
5 | PLAN | Create pilot plan and risk review | Controls implementation risk |  |  | Not Started
6 | DO | Train affected users on the pilot change | Improves adoption and consistency |  |  | Not Started
7 | DO | Run pilot on controlled scope | Tests improvement before full rollout |  |  | Not Started
8 | DO | Capture observations and deviations | Protects learning |  |  | Not Started
9 | CHECK | Compare actual results with baseline and target | Verifies whether change worked |  |  | In Progress
10 | CHECK | Review side effects and stakeholder feedback | Prevents unintended consequences |  |  | Not Started
11 | ACT | Update standard work / SOP / checklist | Locks in the improved method |  |  | Not Started
12 | ACT | Train team on new standard | Supports sustainment |  |  | Not Started
13 | ACT | Define control plan and follow-up audit | Prevents backsliding |  |  | Not Started
14 | ACT | Capture lessons learned and next opportunity | Feeds the next PDCA cycle |  |  | Not Started